## TEAM
USER | LAST NAME | FIRST NAME
Paula | Rodríguez Morales | Paula Rosa
Mauro | Gómez Guillén | Mauro
Santiago | Santana Martínez | Santiago
Acaymo | Granado Sánchez | Acaymo Jesús

## WBS
TASK | SUBTASK | SUBTASK ESTIMATE | SUBTASK DURATION | STAGE | TASK ESTIMATE | TASK DURATION
R0 |  |  |  | 1 | 8:00 | 8:00
| Description | 8:00 | 8:00 | 1
R1 |  |  |  | 2 | 8:00 | 8:00
| Market Analysis | 4:00 | 1:00 | 2
| SWOT Analysis | 4:00 | 7:00 | 2
R2 |  |  |  | 3 | 8:00 | 8:00
| Stories | 8:00 | 8:00 | 3
R3 |  |  |  | 5 | 16:00 | 26:00
| User story estimation and priority | 8:00 | 8:00 | 5
| ProjectLibre | 8:00 | 18:00 | 5
R4 |  |  |  | 6 | 8:00 | 8:00
| Cost estimation | 8:00 | 8:00 | 6
Aplication |  |  |  | 9 | 170:00 | 262:00
| Mock - Ups | 12:00 | 12:00 | 9
| DB Structure Draft Version 1 | 4:00 | 3:00 | 9
| Studying Django | 4:00 | 0:00 | 9
| Backend-First Steps | 8:00 | 12:00 | 9
| Skin Design | 4:00 | 2:00 | 9
| Frontend-First Steps | 8:00 | 30:00 | 9
| Backend developing DB functions | 4:00 | 10:00 | 9
| Frontend developing components | 6:00 | 16:30 | 9
| Fronted conecting routes | 9:00 | 15:00 | 9
| Frontend Trading and Inventory | 6:00 | 12:00 | 9
| Frontend shop screen first steps | 2:00 | 4:00 | 9
| Frontend shop screen finished | 2:00 | 4:00 | 9
| Fixes and visual enhancements | 6:00 | 10:00 | 9
| Started profile screen | 2:00 | 4:00 | 9
| Started Questionarie | 6:00 | 6:00 | 9
| Questionnarie Done | 4:00 | 4:00 | 9
| Creating endpoints | 2:00 | 2:00 | 9
| Changes in backend for user creation | 4:00 | 4:00 | 9
| Endpoints for inventory and foodbar | 4:00 | 8:00 | 9
| Food Trade and Wardrobe endpoints | 6:00 | 3:30 | 9
| Create food trade creation logic | 4:00 | 4:00 | 9
| Shop update | 3:00 | 2:00 | 9
| Create trade search and trade working | 4:00 | 3:00 | 9
| Profile and project fixes | 4:00 | 14:00 | 9
| Pet creation | 8:00 | 10:00 | 9
| Changing pet image depending on player | 4:00 | 3:00 | 9
| Started Questionarie and fixes to pet | 4:00 | 11:00 | 9
| Questionnarie rewards done | 4:00 | 11:00 | 9
| enhanced sign in view | 7:00 | 6:30 | 9
| enhanced login view | 7:00 | 6:30 | 9
| inventory visual changes | 6:00 | 4:00 | 9
| Loading screen and adding real questions | 4:00 | 8:00 | 9
| Pet accessories | 2:00 | 2:00 | 9
| Profile buttons and fixes | 2:00 | 1:00 | 9
| Reset password | 4:00 | 6:00 | 9

## TRACKING
DATE | STARTING TIME | FINAL TIME | TASK | SUBTASK | AUTHOR | DURATION | NOTES
2025-02-04 | 18:00 | 20:00 | R0 | Description | Paula | 2:00
2025-02-04 | 18:00 | 20:00 | R0 | Description | Mauro | 2:00
2025-02-04 | 18:00 | 20:00 | R0 | Description | Santiago | 2:00
2025-02-04 | 18:00 | 20:00 | R0 | Description | Acaymo | 2:00
2025-02-05 | 16:00 | 19:00 | Aplication | Mock - Ups | Mauro | 3:00
2025-02-05 | 16:00 | 19:00 | Aplication | Mock - Ups | Santiago | 3:00
2025-02-05 | 16:00 | 19:00 | Aplication | Mock - Ups | Acaymo | 3:00
2025-02-06 | 10:00 | 13:00 | Aplication | Mock - Ups | Paula | 3:00
2025-02-06 | 17:00 | 18:30 | Aplication | DB Structure Draft Version 1 | Santiago | 1:30
2025-02-06 | 17:00 | 18:30 | Aplication | DB Structure Draft Version 1 | Acaymo | 1:30
2025-02-10 | 21:00 | 23:00 | Aplication | Stutying Django | Mauro | 2:00
2025-02-10 | 21:00 | 23:00 | Aplication | Stutying Django | Santiago | 2:00
2025-02-10 | 21:00 | 23:00 | Aplication | Stutying Django | Acaymo | 2:00
2025-02-10 | 21:00 | 23:00 | Aplication | Stutying Django | Paula | 2:00
2025-02-11 | 18:00 | 19:00 | R1 | Market Analysis | Mauro | 1:00
2025-02-11 | 18:00 | 19:00 | R1 | SWOT Analysis | Mauro | 1:00
2025-02-11 | 18:00 | 19:00 | R1 | SWOT Analysis | Santiago | 1:00
2025-02-11 | 18:00 | 19:00 | R1 | SWOT Analysis | Santiago | 1:00
2025-02-11 | 18:00 | 19:00 | R1 | SWOT Analysis | Paula | 1:00
2025-02-11 | 18:00 | 19:00 | R1 | SWOT Analysis | Paula | 1:00
2025-02-11 | 18:00 | 19:00 | R1 | SWOT Analysis | Acaymo | 1:00
2025-02-11 | 18:00 | 19:00 | R1 | SWOT Analysis | Acaymo | 1:00
2025-02-12 | 17:00 | 20:00 | Aplication | Backend-First Steps | Mauro | 3:00
2025-02-12 | 17:00 | 20:00 | Aplication | Backend-First Steps | Santiago | 3:00
2025-02-12 | 17:00 | 20:00 | Aplication | Backend-First Steps | Acaymo | 3:00
2025-02-12 | 17:00 | 20:00 | Aplication | Backend-First Steps | Paula | 3:00
2025-02-14 | 19:00 | 21:00 | Aplication | Skin Design | Mauro | 2:00
2025-02-15 | 16:00 | 23:30 | Aplication | Frontend-First Steps | Paula | 7:30
2025-02-15 | 16:00 | 23:30 | Aplication | Frontend-First Steps | Mauro | 7:30
2025-02-15 | 16:00 | 23:30 | Aplication | Frontend-First Steps | Santiago | 7:30
2025-02-15 | 16:00 | 23:30 | Aplication | Frontend-First Steps | Acaymo | 7:30
2025-02-15 | 10:00 | 15:00 | Aplication | Backend developing DB functions | Acaymo | 5:00
2025-02-15 | 10:00 | 15:00 | Aplication | Backend developing DB functions | Santiago | 5:00
2025-02-16 | 16:30 | 22:00 | Aplication | Frontend developing components | Paula | 5:30
2025-02-16 | 16:30 | 22:00 | Aplication | Frontend developing components | Acaymo | 5:30
2025-02-16 | 16:30 | 22:00 | Aplication | Frontend developing components | Santiago | 5:30
2025-02-18 | 18:00 | 20:00 | R2 | Stories | Paula | 2:00
2025-02-18 | 18:00 | 20:00 | R2 | Stories | Mauro | 2:00
2025-02-18 | 18:00 | 20:00 | R2 | Stories | Santiago | 2:00
2025-02-18 | 18:00 | 20:00 | R2 | Stories | Acaymo | 2:00
2025-02-19 | 15:00 | 20:00 | Aplication | Fronted conecting routes | Mauro | 5:00
2025-02-19 | 15:00 | 20:00 | Aplication | Fronted conecting routes | Santiago | 5:00
2025-02-19 | 15:00 | 20:00 | Aplication | Fronted conecting routes | Acaymo | 5:00
2025-02-20 | 17:00 | 21:00 | Aplication | Frontend Trading and Inventory | Mauro | 4:00
2025-02-20 | 17:00 | 21:00 | Aplication | Frontend Trading and Inventory | Santiago | 4:00
2025-02-20 | 17:00 | 21:00 | Aplication | Frontend Trading and Inventory | Acaymo | 4:00
2025-02-21 | 21:00 | 23:00 | Aplication | Frontend shop screen first steps | Paula | 2:00
2025-02-21 | 21:00 | 23:00 | Aplication | Frontend shop screen first steps | Mauro | 2:00
2025-02-23 | 12:00 | 14:00 | Aplication | Frontend shop screen finished | Paula | 2:00
2025-02-23 | 12:00 | 14:00 | Aplication | Frontend shop screen finished | Mauro | 2:00
2025-02-23 | 14:00 | 19:00 | Aplication | Fixes and visual enhancements | Paula | 5:00
2025-02-23 | 14:00 | 19:00 | Aplication | Fixes and visual enhancements | Mauro | 5:00
2025-02-23 | 19:00 | 21:00 | Aplication | Started profile screen | Paula | 2:00
2025-02-23 | 19:00 | 21:00 | Aplication | Started profile screen | Mauro | 2:00
2025-02-24 | 20:00 | 23:00 | Aplication | Started Questionarie | Santiago | 3:00
2025-02-24 | 20:00 | 23:00 | Aplication | Started Questionarie | Acaymo | 3:00
2025-02-25 | 18:00 | 20:00 | R3 | User story estimation and priority | Paula | 2:00
2025-02-25 | 18:00 | 20:00 | R3 | User story estimation and priority | Mauro | 2:00
2025-02-25 | 18:00 | 20:00 | R3 | User story estimation and priority | Acaymo | 2:00
2025-02-25 | 18:00 | 20:00 | R3 | User story estimation and priority | Santiago | 2:00
2025-02-26 | 17:00 | 20:00 | R3 | ProjectLibre | Paula | 3:00
2025-02-26 | 17:00 | 20:00 | R3 | ProjectLibre | Mauro | 3:00
2025-02-26 | 17:00 | 20:00 | R3 | ProjectLibre | Santiago | 3:00
2025-02-26 | 17:00 | 20:00 | R3 | ProjectLibre | Acaymo | 3:00
2025-02-26 | 20:00 | 22:00 | Aplication | Questionnarie Done | Acaymo | 2:00
2025-02-26 | 20:00 | 22:00 | Aplication | Questionnarie Done | Acaymo | 2:00
2025-02-26 | 22:00 | 0:00 | Aplication | Creating endpoints | Santiago | 2:00
2025-02-27 | 17:00 | 19:00 | R3 | ProjectLibre | Mauro | 2:00
2025-02-27 | 17:00 | 19:00 | R3 | ProjectLibre | Santiago | 2:00
2025-02-27 | 17:00 | 19:00 | R3 | ProjectLibre | Acaymo | 2:00
2025-02-27 | 15:00 | 17:00 | Aplication | Changes in backend for user creation | Santiago | 2:00
2025-02-27 | 15:00 | 17:00 | Aplication | Changes in backend for user creation | Acaymo | 2:00
2025-02-27 | 21:00 | 1:00 | Aplication | Endpoints for inventory and foodbar | Acaymo | 4:00
2025-02-27 | 21:00 | 1:00 | Aplication | Endpoints for inventory and foodbar | Santiago | 4:00
2025-02-28 | 17:30 | 19:15 | Aplication | Food Trade and Wardrobe endpoints | Santiago | 1:45
2025-02-28 | 17:30 | 19:15 | Aplication | Food Trade and Wardrobe endpoints | Acaymo | 1:45
2025-03-01 | 22:00 | 0:00 | Aplication | Create food trade creation logic | Santiago | 2:00
2025-03-01 | 22:00 | 0:00 | Aplication | Create food trade creation logic | Acaymo | 2:00
2025-03-02 | 1:00 | 3:00 | Aplication | Shop update | Santiago | 2:00
2025-03-02 | 11:00 | 14:00 | Aplication | Create trade search and trade working | Acaymo | 3:00
2025-03-03 | 13:00 | 20:00 | Aplication | Profile and project fixes | Paula | 7:00
2025-03-03 | 13:00 | 20:00 | Aplication | Profile and project fixes | Mauro | 7:00
2025-03-03 | 17:00 | 22:00 | Aplication | Pet creation | Santiago | 5:00
2025-03-03 | 17:00 | 22:00 | Aplication | Pet creation | Acaymo | 5:00
2025-03-04 | 23:00 | 0:30 | Aplication | Changing pet image depending on player | Acaymo | 1:30
2025-03-04 | 23:00 | 0:30 | Aplication | Changing pet image depending on player | Santiago | 1:30
2025-03-05 | 17:00 | 22:30 | Aplication | Started Questionarie and fixes to pet | Acaymo | 5:30
2025-03-05 | 17:00 | 22:30 | Aplication | Started Questionarie and fixes to pet | Santiago | 5:30
2025-03-06 | 20:00 | 1:30 | Aplication | Questionnarie rewards done | Acaymo | 5:30
2025-03-06 | 20:00 | 1:30 | Aplication | Questionnarie rewards done | Santiago | 5:30
2025-03-06 | 12:00 | 18:30 | Aplication | enhanced sign in view | Mauro | 6:30
2025-03-06 | 12:00 | 18:30 | Aplication | enhanced login view | Paula | 6:30
2025-03-06 | 18:30 | 20:30 | Aplication | inventory visual changes | Mauro | 2:00
2025-03-06 | 18:30 | 20:30 | Aplication | inventory visual changes | Paula | 2:00
2025-03-09 | 20:00 | 22:00 | Aplication | Loading screen and adding real questions | Acaymo | 2:00
2025-03-09 | 20:00 | 22:00 | Aplication | Loading screen and adding real questions | Santiago | 2:00
2025-03-10 | 20:00 | 22:00 | Aplication | Loading screen and adding real questions | Acaymo | 2:00
2025-03-10 | 20:00 | 22:00 | Aplication | Loading screen and adding real questions | Santiago | 2:00
2025-03-11 | 18:00 | 20:00 | R4 | Cost estimation | Mauro | 2:00
2025-03-11 | 18:00 | 20:00 | R4 | Cost estimation | Paula | 2:00
2025-03-11 | 18:00 | 20:00 | R4 | Cost estimation | Acaymo | 2:00
2025-03-11 | 18:00 | 20:00 | R4 | Cost estimation | Santiago | 2:00
2025-03-11 | 22:00 | 0:00 | Aplication | Pet accessories | Acaymo | 2:00
2025-03-12 | 10:00 | 11:00 | Aplication | Profile buttons and fixes | Mauro | 1:00
2025-03-14 | 21:00 | 0:00 | Aplication | Reset password | Acaymo | 3:00
2025-03-14 | 21:00 | 0:00 | Aplication | Reset password | Santiago | 3:00

## HOURS_TASK_SUBTASK
Etiquetas de fila | Suma de DURATION
(en blanco) | 0:00
(en blanco) | 0:00
R0 | 8:00
Description | 8:00
Aplication | 262:00
Mock - Ups | 12:00
DB Structure Draft Version 1 | 3:00
Stutying Django | 8:00
Backend-First Steps | 12:00
Skin Design | 2:00
Frontend-First Steps | 30:00
Backend developing DB functions | 10:00
Frontend developing components | 16:30
Fronted conecting routes | 15:00
Frontend Trading and Inventory | 12:00
Frontend shop screen first steps | 4:00
Frontend shop screen finished | 4:00
Fixes and visual enhancements | 10:00
Started profile screen | 4:00
Started Questionarie | 6:00
Questionnarie Done | 4:00
Creating endpoints | 2:00
Changes in backend for user creation | 4:00
Endpoints for inventory and foodbar | 8:00
Food Trade and Wardrobe endpoints | 3:30
Create food trade creation logic | 4:00
Shop update | 2:00
Create trade search and trade working | 3:00
Profile and project fixes | 14:00
Pet creation | 10:00
Changing pet image depending on player | 3:00
Started Questionarie and fixes to pet | 11:00
Questionnarie rewards done | 11:00
enhanced sign in view | 6:30
enhanced login view | 6:30
inventory visual changes | 4:00
Loading screen and adding real questions | 8:00
Pet accessories | 2:00
Profile buttons and fixes | 1:00
Reset password | 6:00
R1 | 8:00
Market Analysis | 1:00
SWOT Analysis | 7:00
R2 | 8:00
Stories | 8:00
R3 | 26:00
User story estimation and priority | 8:00
ProjectLibre | 18:00
R4 | 8:00
Cost estimation | 8:00
Total general | 320:00

## HOURS_PERSON_TASK
Suma de DURATION | Tarea
Etiquetas de fila | (en blanco) | R0 | Aplication | R1 | R2 | R3 | R4 | Total general
Acaymo |  | 2:00 | 82:45 | 2:00 | 2:00 | 7:00 | 2:00 | 97:45
Mauro |  | 2:00 | 54:00 | 2:00 | 2:00 | 7:00 | 2:00 | 69:00
Paula |  | 2:00 | 47:30 | 2:00 | 2:00 | 5:00 | 2:00 | 60:30
Santiago |  | 2:00 | 77:45 | 2:00 | 2:00 | 7:00 | 2:00 | 92:45
(en blanco) | 0:00 | [6 empty] | 0:00
Total general | 0:00 | 8:00 | 262:00 | 8:00 | 8:00 | 26:00 | 8:00 | 320:00

## HOURS_PERSON_DAY
Suma de DURATION | Miembro
Etiquetas de fila | Acaymo | Mauro | Paula | Santiago | (en blanco) | Total general
04-feb | 2:00 | 2:00 | 2:00 | 2:00 |  | 8:00
05-feb | 3:00 | 3:00 |  | 3:00 |  | 9:00
06-feb | 1:30 |  | 3:00 | 1:30 |  | 6:00
10-feb | 2:00 | 2:00 | 2:00 | 2:00 |  | 8:00
11-feb | 2:00 | 2:00 | 2:00 | 2:00 |  | 8:00
12-feb | 3:00 | 3:00 | 3:00 | 3:00 |  | 12:00
14-feb |  | 2:00 |  |  |  | 2:00
15-feb | 12:30 | 7:30 | 7:30 | 12:30 |  | 40:00
16-feb | 5:30 |  | 5:30 | 5:30 |  | 16:30
18-feb | 2:00 | 2:00 | 2:00 | 2:00 |  | 8:00
19-feb | 5:00 | 5:00 |  | 5:00 |  | 15:00
20-feb | 4:00 | 4:00 |  | 4:00 |  | 12:00
21-feb |  | 2:00 | 2:00 |  |  | 4:00
23-feb |  | 9:00 | 9:00 |  |  | 18:00
24-feb | 3:00 |  |  | 3:00 |  | 6:00
25-feb | 2:00 | 2:00 | 2:00 | 2:00 |  | 8:00
26-feb | 7:00 | 3:00 | 3:00 | 5:00 |  | 18:00
27-feb | 8:00 | 2:00 |  | 8:00 |  | 18:00
28-feb | 1:45 |  |  | 1:45 |  | 3:30
01-mar | 2:00 |  |  | 2:00 |  | 4:00
02-mar | 3:00 |  |  | 2:00 |  | 5:00
03-mar | 5:00 | 7:00 | 7:00 | 5:00 |  | 24:00
04-mar | 1:30 |  |  | 1:30 |  | 3:00
05-mar | 5:30 |  |  | 5:30 |  | 11:00
06-mar | 5:30 | 8:30 | 8:30 | 5:30 |  | 28:00
09-mar | 2:00 |  |  | 2:00 |  | 4:00
10-mar | 2:00 |  |  | 2:00 |  | 4:00
11-mar | 4:00 | 2:00 | 2:00 | 2:00 |  | 10:00
12-mar |  | 1:00 |  |  |  | 1:00
14-mar | 3:00 |  |  | 3:00 |  | 6:00
(en blanco) |  |  |  |  | 0:00 | 0:00
Total general | 97:45 | 69:00 | 60:30 | 92:45 | 0:00 | 320:00